## business requirement
Business requirement
1 | Create a json file based on user information.
2 | User input can be structured or unstructured.
3 | Json file should be in required and specific format.
4 | Create user and assistant chatspace.
5 | Create multiple users and handle their instances.
6 | Save the user-specific prompt and responses in postgres database.
7 | Show conversation history in the chatspace.
8 | Create User Form based on the output json

## Architecture
ARCHITECTURE
Making the Model | Preparing the data |  | Fine-tuning/Training | Incremental Fine-tuning to handle missing data
| python, json |  | python, openai
json
Chatspace | Creating endpoints |  | User's instance management |  | Connecting to postgres database
| flask |  | flask, postman, openai |  | psychopg2
Creating UI for user-assistant chatspace
flask, css

## sections
SECTIONS
Making the Model
1 | Prepare the data
2 | Format data according to need
3 | Fine-tune gpt-3.5-turbo using the prepared data
4 | Incremental fine-tune to handle missing inputs
5 | Testing
Chatspace
1 | Creating required endpoints
2 | Connecting created gpt-model
3 | Manage user's and chat's sessions
4 | Connecting and storing prompt-responses to postgres database
5 | Displaying chat history of respective users in their respective chatspace
6 | Making the UI of the user-assistant chatspace
User Form
1 | Create user Form based on the output json
2 | Group conditions together
3 | Textboxes to add rules and groups manually

## tasks
TASKS
Creating all endpoints
1 | Create all the endpoints that will be required and used using flask.
2 | First create the interface endpoint that will ask for the user selection.
3 | Create a navigation endpoint that will navigate to the selected user's chatspace.
4 | Create user's endpoint that will have the chatspace components.
5 | Create a database endpoint if necessary to show the chat history of the user-assistant.
Managing user sessions
1 | Manage different and separate user-assistant sessions for each user.
2 | Also manage the chat session with the trained gpt-model to hold the context of the particular session.
3 | Try using session parameters and postman to do it.
4 | Format of the json object that is returned in the response.
Connecting database
1 | Connect to postgres database using psycopg2 and SQLAlchemy.
2 | Store the user's prompts and assistant's responses in the database.
3 | Each user's conversations should be stored in user-separate tables.
Creating UI
1 | Create good UI for user-assistant chatspace
2 | First apply good theme for the page
3 | Add dark/light mode button based
4 | Take reference from chatgpt UI
5 | Make the user chatbox of proper size
6 | The chat history should be in tablular format
7 | There should be a button like thing to zoom for each response
that assistant gives and on click of that button, the json file
should get displayed in the desired and specific format
8 | Also add timestamps to each conversation pair in chat history
Show session respective chat history
1 | Show the chat conversation of the particular session
2 | It should be below the user-assistant chat-boxes
3 | The chat history should be in user-assistant format
UI updates
1 | The window that opens upon clicking zoom, that should be resized and movable.
2 | The response in that window should be in json format
3 | On clicking submit in light-mode, the response should be generated in light mode only
4 | User prompt border, user text, assistant text, etc's color should change in light mode
5 | Select users page
6 | Timestamp and zoom button overlaping text in chat-history
7 | Add timestamp to 'show database' page as well.
8 | Selected mode (light/dark) should persist even while navigating between different pages
9 | Try to implement add user functionality, where clicking on add user button, it will ask username
10 | Add a CLEAR button, to clear the prompt of the user before submitting.
11 | Add a download button to download the response of the assistant.
12 | Enable voice typing for prompts
13 | Add a button to copy the assistant's response
14 | The chat history should be shown in tabular format
15 | The mic button on clicking gets own for a limited time only, modify it to remain on until
button is clicked again.
Handling UI errors
1 | Handling Text overlap below MIC button
| Take user prompt | Create JSON file | Based on JSON, create user Form
User Form
1 | replace the current field names with output json fields
2 | The field name options should contain the indicators, whose params are
mentioned
3 | The field name should be able to take any new indicator name, not hardcoded
4 | If any indicators have periods, there should be textboxes to select period size
5 | Make the UI better of the user form
6 | Getrules button should display the entire json used to create the user form
7 | Manage operators : (less, greater, >, <)
8 | Except numbers all output fields should be drop-down lists
9 | Make the close comparison field correct
10 | Integrate the newly made json with the json generated by the assistant
1 | Dynamically input select option values from the indicator's section from the json
2 | Make the input fields dynamic to fetch any kind of condition and create fields on it
1 | Train the model again to handle MACD reversal strategy.
Login/Signup
1 | Create a login/signup form for user.
2 | User-specific sessions should be created based on user tokens.
3 | Store the username and password in database.
4 | Also add functionality of signup with google.
GUI changes
1 | Add loading css when page is loading
2 | Add messages on the screen when the user is redirected
3 | Add logout functionality.